## Slide 1: Information Technology Capstone CIS498
The Project Office
Notes: Welcome to Information Technology Capstone.
In this lesson we will discuss The Project Office.
Next slide.

## Slide 2: Topics
Sypris Electronics
Vitalize Consulting Solutions (VCS), Inc.
Churchill Downs Incorporated (CDI): Establishing a PMO
Churchill Downs Incorporated (CDI): Managing Scope Changes
Types of Project OfficesStarting up a PMO and Considerations
Computer Sciences Corporation (CSC)
Understanding the Nature of a PMO
DTE Energy
Exel
Hewlett-Packard
EDS
Notes: The following topics will be covered in this lesson:
Sypris Electronics;
Vitalize Consulting Solutions (VCS), Inc.;
Churchill Downs Incorporated, or CDI, Establishing a PMO;
Churchill Downs Incorporated, or CDI, Managing Scope Changes;
Types of Project Offices. Starting up a PMO and Considerations;
Computer Sciences Corporation, or CSC,;
Understanding the Nature of a PMO;
DTE Energy;
Exel;
Hewlett-Packard; and
EDS.
Next slide.

## Slide 3: Topics, Continued
Star Alliance
Importance of a PMO in Local Government
Project Audits and the PMO
Project Health Checks
Critical Ratio as an Indicator of the Health of a Project
PMO of the Year Award
Notes: Additionally, the following topics will be covered in this lesson:
Star Alliance;
Importance of a PMO in Local Government;
Project Audits and the PMO;
Project Health Checks;
Critical Ratio as an Indicator of the Health of a Project; and
PMO of the Year Award;
Next slide.

## Slide 4: Sypris Electronics
PMO has Unique Goals and Objectives
PMO has Main Functions
Notes: Sypris Electronics, like every other company, has unique goals and objectives for their PMO. These differing goals and objectives cause a company to define functions.
The main functions of a PMO, according to Sypris Electronics are:
One: Project management data archive;
Two: On-going training in project management;
Three: State-of-the-art procedures and guidelines;
Four: Promote consistency and uniformity in project management;
Five: Centralized point of reference for project management;
Six: Specialized skills and knowledge education;
Seven: Best practices repository;
Eight: Personnel bench strength;
Nine: Mentor novice team members; and
Ten: Consultation and advisement.
Next slide.

## Slide 5: Vitalize Consulting Solutions (VCS), Inc.
Direct Link to Executive Leadership
One Methodology or Standard
Notes: VCS uses the PMO and has the home base for project management consultants. In addition, the PMO has a direct link to the executive level of the organization. This is a key factor because the PMO must be taken seriously within the organization and executive support will foster that support.
One of the biggest challenges with a PMO is following one methodology or standard across the organization for multiple initiatives. This in part is due to projects varying in size, scope and complexity. The key to success is making sure the PMO follows a consistent format, provides the tools needed to get the job done but allows for scalability based on the individual project manager’s needs.
Next slide.

## Slide 6: Churchill Downs Incorporated (CDI): Establishing a PMO
Challenge Obstacles
Key Steps
Notes: Deciding to implement a PMO is easy but being able to do it requires that certain obstacles be overcome.
One such obstacle at Churchill Downs was familiarity. The organizational resources had never been exposed to formal project management. Senior management was comfortable with current processes and procedures in spite of knowing that there was a need for a structured, standardized approach to requesting, approving, and managing projects and maintaining the project portfolio.
The PMO was implemented because executives took an active role in the implementation process. This support was important.
Some of the key steps taken were: Developed a three-fold mission focused on the need identified by the senior leadership; Defined the PMO’s business objectives and linked progress to the
PMO Director’s compensation plan; and Conducted training classes on project management, team building, and critical thinking among others.
Next slide.

## Slide 7: Churchill Downs Incorporated (CDI): Managing Scope Changes
Instituted Scope Change Management
Six Steps to Scope Definition and Change Control
Notes: Churchill Downs instituted scope change management procedures. The six steps necessary for scope definition and change control include:
Step One: Be Lean. In this regard a company should define a well-focused scope to avoid the natural resistance to excessive change;
Step Two: Define Preliminary Scope. For a company without processes for capturing the business objectives, one must define a structured approach for documenting, evaluating, and approving the preliminary scope of work;
Step Three: Develop Understanding of What Final Acceptance Means to Project Sponsor or Sponsors. In this step, the sponsor acceptance should be well-defined for stakeholders using plain language;
Step Four: Define, Document, and Communicate a Structured Approach to Requesting, Evaluating, and Approving Change Requests. The process that is use to modify scope should be defined so that all participants are able to use the correct procedures.
Step Five: Document and Validate Full Scope of Work. This step includes creating a work breakdown structure. This will aid in understanding what must be done within the project; and
Step Six: Manage Change. The scope change requests will most certainly flood in but they must be managed according to the procedures that have been implemented.
Next slide.

## Slide 8: Types of Project Offices
Three Types of Project Offices
  Functional
  Customer Group
  Corporate
Notes: There are three Types of Project Offices commonly used in companies.
The first is a Functional Project Office: This type of project office is utilized in one functional area or division of an organization.
The second is Customer Group Project Office: This type of project office is for better customer management and customer communications.
Lastly, there is Corporate or Strategic Project Office: This project office services the entire company and focuses on corporate and strategic issues rather than functional issues.
Next slide.

## Slide 9: Starting up a PMO and Considerations
Strategic Asset
Core Purpose
Notes: When starting up a Project Management Office, one should ensure that the PMO is part of the organization’s strategic plan. The PMO should be considered a strategic asset that helps an organization move toward its goals.
In addition, the PMO should define its core purpose. Understanding why the PMO exists is a good start. The reasons for the PMO should be completely clear with all participants including employees, managers, project managers and executives.
Next slide.

## Slide 10: Computer Sciences Corporation (CSC)
Experienced Individual or Consulting Firm
Best Practices
Notes: When a company wants to start a PMO, the choice, most often is to bring in an expert who has experienced some successes; however, possibly a better choice would be to hire a consulting company to help with the implementation of a PMO. Another reason for hiring a consulting company is that an individual may not be familiar with your industry whereas a consulting company would be better able to meet industry needs and concerns.
Much of the success that is achieved starts with Best Practices. Best Practices are the processes, procedures, standards, methodologies, techniques, activities, etc. that are proven to be more effective and successful in providing measureable efficiencies and results than other comparable processes, procedures, standards, activities, and techniques.
Potential Best Practices are assessed and evaluated throughout the duration of the project life cycle. These are then documented in the Lessons Learned template and made accessible to all organizational employees and team members.
Next slide.

## Slide 11: Understanding the Nature of a PMO
Understand the Purpose of the PMO
Know What the PMO should be
Project Managers Must Guide Companies
Notes: When implementing a PMO, a company must understand the purpose of the PMO is. For instance, is the PMO supposed to be: a Project Management Center of Excellence focusing on process owners; a Governance Office overseeing compliance; a project manager resource pool; or a resource management center charged with balancing supply and demand? Each one of these implementation is different and prior to the start of implementations, a company must define the purpose and goals of the PMO.
Professional project managers must help their companies distinguish the difference in the functional role of each of the different organizations. In addition, the span of control of the PMO must be clarified.
Next slide.

## Slide 12: DTE Energy
Location of PMO with Company
Functions of the PMO
Notes: Normally the Project Office is developed and is most common in the information systems environment. However, the project office can be located in any area of the company. At DTE Energy, the Project Management Office is a function with the Customer Service Program Management group. The Customer Service Program Management group consists of the PMO, the process management team, and the customer contact channel management team.
The PMO provides project management support for the continuous improvement initiatives within the department. These initiatives are designed to achieve the Customer Service Strategy.
Specific functions of the PMO include:
One: Developing and maintaining the project management methodology;
Two: Maintaining the portfolio of Customer Service continuous improvement projects;
Three: Collecting and disseminating project data and metrics; and
Four: Providing project management tools and templates.
Next slide.

## Slide 13: Exel
Multinational
Coordinated Effort
Single-source Solution
Notes: For multinational companies, several project offices can exist that must function in a coordinated effort. Exel uses a global project management office as a project management center of
Excellence supporting project managers from all regions and sections. At Exel, the group provides a single-source solution for Exel’s internal customers who are the sector PMOs and the project managers.
Next slide.

## Slide 14: Hewlett-Packard
Core Skill for HP
Award Winning Program
Specific Activities to be Successful
Notes: Project management is a core skill for Hewlett-Packard. The company has an award winning Project Management Development Program which is organized by core project management courses, advanced project management topics, courses specific to HP Services practices, and professional skills training.
Other activities included:
One: Driving project management certification programs;
Two: Updating and managing the formal training curriculum in coordination with workforce development;
Three: Driving and participating in major events like PMI congresses and regional project management training and networking events;
Four: Encouraging informal communication and mentoring; and
Five: Providing mentorship to field project managers.
Next slide.

## Slide 15: EDS
Oversight For Individual Projects
PMO Used For Facilitation
PMO Adds Functionality
Notes: Most organizations have a PMO established. These companies assume that organizations need to have oversight for their individual projects. The PMO is used for project oversight, status reporting, and project conformance.
For many companies the PMO was created to facilitate transactions where suppliers would handoff solutions to another supplier. The PMO was put in place to manage the handoff and all associated functions and tasks.
The issue with this implementation approach is that there was never a single model developed for this type of framework, so the PMO would add additional constraints, bureaucracy, or workloads.
Next slide.

## Slide 16: Star Alliance
First and Largest Airline Alliance
Each Member has PMO
Star PMO Provides Services
Notes: The Star Alliance is the world’s first and largest airline alliance with twenty-one carriers and four more in the integration process. The Star Alliance network offers more than eighteen thousand one hundred daily flights to nine hundred seventy-five destinations in one hundred sixty-two countries. Each member of the Star Alliance has a PMO. The Star PMO provides project management services across the Star enterprise. The Star PMO carries out for the business units include such topics as information technology, marketing, sales, products, services, and frequent flyer programs as well as common sourcing projects.
Next slide.

## Slide 17: Importance of a PMO in Local Government
PMO Not Just for Large Corporations
Adherence to PMBOK
Realistic Measures
Notes: A PMO is not restricted to large corporations. The PMO concept in recent years has spread to all levels of government. In government the PMO may report to the chief information officer.
The PMO follows the model published by the Project Management Institute’s Project Management Body of Knowledge which is the guide for project management.
Project success is measured on a number of factors including adherence to time and budget constraints, calculation of earned value and customer feedback throughout the project.
Next slide.

## Slide 18: Project Audits and the PMO
Independent Review
Types of Audits
Notes: Over the past years, the necessity for a structured independent review of various parts of a business, including projects, has become immensely important to organizational success. Some of this focus can be attributed to the Sarbanes-Oxley Law compliance requirements. Most often, this compliance responsibility is given to the PMO who has oversight.
Several common types of audits include:
Performance Audits: These audits are used to appraise the progress and performance of a given project;
Compliance Audits: These audits are usually performed by the PMO to validate that the project is using the project management methodology properly; and
Quality Audits: These audits ensure that the planned project quality is being met and that all laws and regulations are being followed;
Exit Audits: These audits are usually for projects that are in trouble and my need to be terminated; and
Best Practices Audits: These audits can be conducted at the end of each life-cycle phase or at the end of the project.
Next slide.

## Slide 19: Project Health Checks
Health Checks
Hydra Sessions
Notes: Quite often, projects undergo health checks, but by people who are not truly qualified to conduct them. The concept of performing a health check is a sound practice provided the right people are performing the health check and the right information is being discussed.
The purpose of the health check should be to provide constructive criticism and evaluate alternative approaches as necessary. Too often, meetings end up being a personal attack on the project team.
A more frequent used alternative approach to health checks is called the multi-brained project manager or as it is sometimes referred, a Hydra project manager. The reason for using this approach rather than a simple peer review approach is to overcome the one –shot input while also showing the added value opportunity.
Hydra sessions take a large investment of time to setup because project managers from across the company are participating in the review.
Next slide.

## Slide 20: Critical Ratio as an Indicator of the Health of a Project
Product of Schedule Performance and Cost Performance Index
Thresholds Must be Set
Notes: The critical ratio is the product of Schedule Performance Index and Cost Performance Index. The ratio is usually calculated by an enterprise project management tool such as Microsoft Office
Project Server. By setting the thresholds of this value for different levels of project health for example, Green, Yellow, and Red, MS Project will calculate the health for you.
Critical Ratio is easy to determine and with some simple formulas, rules, and thresholds that you set, can provide a valuable measure of overall health.
Next slide.

## Slide 21: PMO of the Year Award
PMO is Most Significant Change
Center for Business Practices Started
Notes: It is believed by many that the most significant change in project management is the establishment of the PMO concept. As such, it is no big surprise that The Center for Business Practices initiated the PMO of the Year award. The PMO of the Year Award is presented to the PMO that best illustrates, through an essay and other documentation, their project management improvement strategies, best practices, and lessons learned.
Next slide.

## Slide 22: Summary
Sypris Electronics
Vitalize Consulting Solutions (VCS), Inc.
Churchill Downs Incorporated (CDI): Establishing a PMO
Churchill Downs Incorporated (CDI): Managing Scope Changes
Types of Project Offices
Starting up a PMO and Considerations
Computer Sciences Corporation (CSC)
Understanding the Nature of a PMO
DTE Energy
Exel
Hewlett-Packard
EDS
Notes: We have now reached the end of this lesson. Let’s take a look at what we’ve covered:
First we covered Sypris Electronics who has unique goals and objectives for their PMO which caused them to create a list of PMO main functions;
Next, Vitalize Consulting Solutions, or VCS, Inc. supports the PMO having a direct link to executive leadership and embracing one methodology or standard within the company;
Next, Churchill Downs Incorporated, or CDI: Establishing a PMO focused on challenging obstacles and key steps to make the transition;
Next, Churchill Downs Incorporated, or CDI: Managing Scope Changes explains the need to have instituted Scope Change Management Procedures. There was also discussion of the Six Steps to Scope Definition and Change Control; and
Next, the three Types of Project Offices were covered.
Starting up a PMO and Considerations deals with treating the PMO as a strategic asset, and defining and understanding the core purpose;
Next, Computer Sciences Corporation, or CSC, discusses using an experienced individual or Consulting Firm and the use of Best Practices to start a PMO;
Next, Understanding the Nature of a PMO covered understanding the purpose of the PMO, knowing what the PMO should be, and why project managers must guide companies;
Next, DTE Energy topic covered the Location of the PMO and the company functions of the PMO;
Next, Exel which is a multinational corporation focuses on a coordinated effort and a single-source solution for project managers;
Next, Hewlett-Packard we learned that HP treats project management as a core skill. The program is award winning and focuses on specific activities to be successful; and
Next, the EDS topic covered oversight for individual projects, how the PMO could be used for facilitation, and how functionality must be added when the PMO is used for facilitation;
Next slide.

## Slide 23: Summary, continued
Star Alliance
Importance of a PMO in Local Government
Project Audits and the PMO
Project Health Checks
Critical Ratio as an Indicator of the Health of a Project
PMO of the Year Award
Notes: Additionally, the following topics were covered in this lesson:
Star Alliance which is the first and largest airline alliance. Each Member has PMO and the Star PMO Provides Services to all members;
Then, the Importance of a PMO in Local Government was addressed by covering the fact that PMOs are not just for large corporations. Government usually adheres to the project management book of knowledge which relates projects to realistic measures;
Next, Project Audits and the PMO covered independent review and the types of audits;
Next, Project Health Checks were discussed and focused on project Health Checks and Hydra Sessions;
Next, Critical Ratio as an Indicator of the Health of a Project covered definition of critical ratio and emphasized that thresholds must be set; and
Lastly we covered the PMO of the Year Award which noted that the PMO concept is the Most Significant Change of the twenty-first century and that the award was started by the Center for Business Practices.
This concludes this lesson.